## Start here
Empower manual quoting kit: timed pilot test
What this is
A test of the Empower Ops Agents app against the way quotes are made today. You will quote one client request twice: first by hand with this workbook, then with the app. We time both and you judge both. Your honest opinion is the point; there are no wrong answers.
All people, projects and rates here are DEMO data that look like Empower's, not real. Judge the method and the result as if they were real.
Part 1: quote it by hand (up to 40 minutes)
1. Write the start time in 'Scorecard' (cell C6) and read 'Client request'.
2. Work out the hours per role, a team and dates, and a price, the way you normally would. Fill the yellow cells in 'Quote worksheet'. It adds PM, tech lead, QA and contingency from the policy and does the price and margin sums for you.
3. Use the reference sheets as you would your own files: 'Rate card & policy', 'People & availability' (who is free each week), 'Module history' (what past modules actually took) and 'Past projects'.
4. Also note feasibility, the top risks and the questions you would ask the client.
5. Stop at a quote you would be willing to discuss internally, or at 40 minutes. Write the end time (C7). If you stopped early, write how long a proper quote would really take you (C8).
Part 2: the same request in the app (about 15 minutes)
6. In the app, sign in as Director, open 'New deal', click the sample PDF 'brightsmile_rfp.pdf' (same request), and press 'Run Deal Desk'. Write the start time (C10) when you press Run.
7. When it finishes (about 2-3 minutes), read the tabs Overview, Estimate, Team & timeline, Pricing, Review, Proposal. Write the time when you have formed a view (C11).
8. Record your decision at the bottom of the Overview tab (Approve to send, Request changes or Reject), and fill 'Hours this quote takes by hand' and 'Draft quality (1-5)'.
Part 3: score both (about 10 minutes)
9. Fill the 'Scorecard' sheet: rate your quote and the app's on each line, then answer the questions at the bottom.
How to read this workbook
Yellow cell with blue text = type here. Black = calculated (don't edit). Green = pulled from another sheet.
Example of the format: in 'Quote worksheet', Backend Developer build hours = 640 (a number of hours, not a %).

## Client request
The client request (identical to the sample PDF in the app)
Client | BrightSmile Dental Group
Country | US
Quote currency | USD
Received | 2026-10-26 (the demo data's 'today')
RFP (text of the PDF) | BrightSmile Dental Group - Request for Proposal: Patient Booking App Issued by: Megan Walsh, COO, BrightSmile Dental Group (Ohio and Michigan, USA) Background and needs Hi Empower team, We run 14 dental clinics across Ohio and Michigan (BrightSmile Dental Group). Right now patients call the front desk to book, and our staff spend most of the morning on the phone. We want: 1. A patient app (iPhone + Android) and a matching website where patients can book, reschedule and cancel cleanings and appointments with a specific dentist or hygienist. 2. SMS and email reminders 48h and 2h before the visit, with a 'confirm' button. No-shows cost us a lot. 3. Patients should see their upcoming visits, past visit summaries and outstanding balance, and pay the balance by card. 4. A simple admin panel for front-desk staff to manage dentist schedules, block holidays and see the day's bookings per clinic. 5. Our practice management system is Dentrix; bookings need to sync with it (they have an API, we think). We obviously need this to be HIPAA compliant. We'd like to go live before our busy season in early April. Budget is not fixed but our board was thinking around $60-80k. Can you send a proposal with timeline and price? Thanks, Megan Walsh COO, BrightSmile Dental Group Evaluation Proposals will be compared on understanding of our needs, HIPAA approach, timeline, team and price. Please include assumptions and questions for us.

## Quote worksheet
Your quote: BrightSmile patient booking app
Yellow = type here (blue text). Black = calculated. Green = pulled from 'Rate card & policy'.
Quote currency | USD | USD, EUR or GBP
Risk level | medium | low, medium or high: sets contingency (10% / 15% / 25%)
Regulated data (HIPAA / PCI / GDPR)? | No | Yes adds 10% to QA hours
Discount | 0% | Type 5% (or 0.05). Over 5% needs a director; 10% is the maximum
Planned start date |  | e.g. 2 Nov 2026
Planned go-live date |  | e.g. 30 Apr 2027
Feasible? |  | Yes / Yes with conditions / No
Weeks from start to go-live
Role | Build hours (you enter) | Hours incl. PM, lead, QA, contingency | Rate / h | Billing at list | Internal cost / h (INR) | Internal cost (INR)
Business Analyst | 0 | [5 empty] | ba
UI/UX Designer | 0 | [5 empty] | uiux
Frontend Developer | 0 | [5 empty] | fe
Backend Developer | 0 | [5 empty] | be
Mobile Developer | 0 | [5 empty] | mobile
QA Engineer | 0 | [5 empty] | qa
DevOps / Cloud Engineer | 0 | [5 empty] | devops
Data / BI Engineer | 0 | [5 empty] | data
AI / ML Engineer | 0 | [5 empty] | ml
Project Manager | added by policy | [5 empty] | pm
Tech Lead / Architect | added by policy | [5 empty] | lead
Total
How the hours are built up (policy rules)
Development hours (FE, BE, mobile, DevOps, data, ML)
QA needed (minimum share of dev hours)
QA top-up to reach the minimum
Regulated-data QA uplift
Base hours (build + QA top-ups)
Project manager
Tech lead
Subtotal (expected hours)
Contingency %
Total hours priced
Scale factor (total / subtotal)
Price and margin
Time & materials at list rates
Time & materials price (after discount, rounded)
Fixed price (list + risk premium, after discount, rounded)
Internal delivery cost (in quote currency)
Margin, fixed price
Margin, time & materials
Policy check
Which would you recommend?
Team you would staff (names or roles)
Top risks
Questions you would ask the client before quoting
Note on C5: USD, EUR or GBP
Note on C6: low, medium or high: sets contingency (10% / 15% / 25%)
Note on C7: Yes adds 10% to QA hours
Note on C8: Type 5% (or 0.05). Over 5% needs a director; 10% is the maximum
Note on C9: e.g. 2 Nov 2026
Note on C10: e.g. 30 Apr 2027
Note on C11: Yes / Yes with conditions / No
Note on C49: Fixed price or Time & materials

## Scorecard
Scorecard: time and quality, by hand vs the app
Yellow = type here. Times as hh:mm (e.g. 14:05). Ratings 1 (poor) to 5 (excellent).
Timing | Time |  | Note
Part 1 by hand: start
Part 1 by hand: end
If you stopped early: hours a proper quote would really take you |  |  | Only if you stopped at the 40-minute limit
Minutes spent by hand
Part 2 app: start (pressed Run)
Part 2 app: formed a view
Minutes with the app (run + reading)
How many days does a quote like this usually take at Empower, from email to sending? |  |  | Ask yourself, not the app
Rate each quote (1-5) | By hand | App | Why (what was missing or wrong?)
Example: Hours are realistic (format only) | 3 | 4 | App's mobile hours look high; mine missed QA
Hours are realistic for this work
Team and dates are realistic (people actually free)
Price is right for this client and within policy
Risks and gaps were caught (e.g. Dentrix, HIPAA, deadline, budget)
Questions for the client are the right ones
Ready to send to the client after light editing
Average
Questions | Answer
Minutes of editing the app's proposal would need before you'd send it
Would you use this for real quotes? (1 = never, 5 = every time)
What did the app get wrong, or what would you not trust?
What was most useful?
One sentence I may quote in my course report
May I quote you as (name + role, role only, or no)?
Your role at Empower

## Rate card & policy
Rate card and pricing policy (demo)
Billing rate per hour
Role key | Role | USD | EUR | GBP | Internal cost / h (INR) | Policy | Value
pm | Project Manager | 38 | 36 | 31 | 1726.4 | INR per USD | 88
ba | Business Analyst | 32 | 30 | 26 | 1060.3 | INR per EUR | 102
uiux | UI/UX Designer | 30 | 28 | 25 | 1075.4 | INR per GBP | 117
fe | Frontend Developer | 28 | 27 | 23 | 966.3 | PM overhead | 10%
be | Backend Developer | 30 | 29 | 25 | 1272.4 | Tech lead overhead | 6%
mobile | Mobile Developer | 32 | 30 | 26 | 802 | Minimum QA (share of dev hours) | 20%
qa | QA Engineer | 22 | 21 | 18 | 1189.8 | Extra QA for regulated data (HIPAA/PCI/GDPR) | 10%
devops | DevOps / Cloud Engineer | 36 | 34 | 29 | 885.1 | Contingency: low risk | 10%
data | Data / BI Engineer | 36 | 34 | 29 | 1051.2 | Contingency: medium risk | 15%
ml | AI / ML Engineer | 45 | 42 | 37 | 927.4 | Contingency: high risk | 25%
lead | Tech Lead / Architect | 45 | 42 | 37 | 2186.3 | Fixed-price risk premium | 12%
Billing rates per hour from the demo rate card (data/seed/rate_card.json, as of 2026-10-01). | [5 empty] | Margin floor | 35%
[6 empty] | Target margin | 50%
[6 empty] | Discount without director approval (max) | 5%
[6 empty] | Maximum discount | 10%
[6 empty] | Discovery weeks | 2
[6 empty] | Stabilisation weeks | 2
[6 empty] | Warranty (days) | 60
[6 empty] | Hours per week | 40
Fixed-price payment milestones
[6 empty] | Contract signature (mobilisation) | 20%
[6 empty] | Design + architecture sign-off | 20%
[6 empty] | Beta / UAT release | 40%
[6 empty] | Go-live | 20%
T&M billing: Monthly in arrears against approved timesheets
Note on G4: Average loaded monthly cost of people in this role x 1.45 overhead / 160 hours (same formula the app uses). Internal only.

## People & availability
People and free capacity per week (demo). 100 = fully free; planned leave counts as busy.
ID | Name | Role | Title | Level | Office | Years | Skills | 26 Oct | 02 Nov | 09 Nov | 16 Nov | 23 Nov | 30 Nov | 07 Dec | 14 Dec | 21 Dec | 28 Dec | 04 Jan | 11 Jan
E005 | Aditya Deshmukh | ba | Mid Business Analyst | Mid | Indore | 4 | User stories, Power BI, Process mapping, Healthcare domain | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0
E006 | Yash Bhatt | ba | Senior Business Analyst | Senior | Pune | 11 | Figma, SQL, Healthcare domain, User stories, Power BI | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E007 | Swati Solanki | ba | Mid Business Analyst | Mid | Bhopal | 6 | Requirements, Fintech domain, Process mapping, Power BI | 50 | 50 | 50 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
E019 | Vivek Porwal | be | Senior Backend Developer | Senior | Indore | 9 | Salesforce API, Redis, Django, FastAPI, Node.js | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
E020 | Rahul Parmar | be | Senior Backend Developer | Senior | Indore | 9 | ASP.NET MVC, REST APIs, Stripe, .NET Core, WebSockets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
E021 | Tushar Nair | be | Senior Backend Developer | Senior | Indore | 6 | .NET Core, PostgreSQL, SQL Server, GraphQL, Elasticsearch | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
E022 | Tanvi Solanki | be | Mid Backend Developer | Mid | Bhopal | 3 | Python, .NET Core, Redis, Django | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 50 | 50
E023 | Pooja Dixit | be | Senior Backend Developer | Senior | Indore | 6 | C#, WebSockets, MongoDB, Python, Twilio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E024 | Pooja Sharma | be | Senior Backend Developer | Senior | Pune | 11 | PostgreSQL, Python, ASP.NET MVC, Twilio, SQL Server | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E025 | Pooja Tiwari | be | Mid Backend Developer | Mid | Bhopal | 5 | Python, Stripe, ASP.NET MVC, Twilio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100
E026 | Akash Rajput | be | Mid Backend Developer | Mid | Indore | 3 | .NET Core, GraphQL, ASP.NET MVC, C# | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E027 | Aditya Patil | be | Mid Backend Developer | Mid | Indore | 4 | ASP.NET MVC, REST APIs, Python, Twilio | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 100 | 100
E028 | Karan Rao | be | Senior Backend Developer | Senior | Pune | 8 | SQL Server, Salesforce API, Python, Redis, GraphQL | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E045 | Varsha Patidar | data | Mid Data / BI Engineer | Mid | Pune | 6 | SQL, Power BI, Snowflake, Spark | 100 | 100 | 100 | 100 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E046 | Pooja Kothari | data | Mid Data / BI Engineer | Mid | Indore | 6 | Airflow, Spark, ETL, SQL | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 100 | 100 | 100 | 100
E047 | Ankit Patidar | data | Mid Data / BI Engineer | Mid | Indore | 3 | Power BI, Tableau, AWS Glue, SQL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100
E042 | Nikhil Parmar | devops | Junior DevOps / Cloud Engineer | Junior | Pune | 1 | CI/CD, Docker, Serverless | 75 | 75 | 75 | 75 | 0 | 0 | 75 | 75 | 75 | 75 | 75 | 75
E043 | Aarav Soni | devops | Junior DevOps / Cloud Engineer | Junior | Indore | 2 | AWS, Monitoring, Kubernetes | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 100 | 100 | 100 | 100
E044 | Naveen Rajput | devops | Senior DevOps / Cloud Engineer | Senior | Indore | 11 | Serverless, Terraform, Monitoring, Kubernetes, Azure | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
E011 | Jayesh Chouhan | fe | Mid Frontend Developer | Mid | Pune | 4 | Angular, Next.js, Redux, WordPress | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
E012 | Komal Sinha | fe | Junior Frontend Developer | Junior | Pune | 3 | TypeScript, Angular, Accessibility (WCAG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E013 | Omkar Goyal | fe | Mid Frontend Developer | Mid | Bhopal | 3 | Next.js, Vue, Accessibility (WCAG), TypeScript | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E014 | Mohit Shukla | fe | Mid Frontend Developer | Mid | Bhopal | 4 | Vue, Tailwind, WordPress, Next.js | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
E015 | Mohit Kaur | fe | Senior Frontend Developer | Senior | Bhopal | 7 | React, Next.js, Vue, TypeScript, Angular | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E016 | Nidhi Parmar | fe | Mid Frontend Developer | Mid | Indore | 6 | TypeScript, Vue, Redux, Tailwind | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 100 | 100
E017 | Rakesh Gupta | fe | Senior Frontend Developer | Senior | Pune | 9 | Accessibility (WCAG), React, WordPress, Tailwind, Next.js | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
E018 | Pooja Dubey | fe | Junior Frontend Developer | Junior | Indore | 3 | Next.js, Redux, Tailwind | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E051 | Vikram Gupta | lead | Tech Lead / Architect | Lead | Pune | 16 | .NET Core, Node.js, Security, Python, Microservices, Azure | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
E052 | Manish Goyal | lead | Tech Lead / Architect | Lead | Indore | 14 | Python, Node.js, Azure, React, .NET Core, System design | 50 | 50 | 50 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
E053 | Komal Gupta | lead | Tech Lead / Architect | Lead | Indore | 12 | Azure, Microservices, Security, AWS, React, .NET Core | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 50 | 50
E054 | Nidhi Raghuwanshi | lead | Tech Lead / Architect | Lead | Bhopal | 12 | Security, .NET Core, System design, Microservices, React, AWS | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 50 | 50 | 50 | 50
E048 | Swati Malviya | ml | Mid AI / ML Engineer | Mid | Indore | 5 | MLOps, Python, Vector databases, LLM / RAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
E049 | Manish Choudhary | ml | Mid AI / ML Engineer | Mid | Indore | 6 | OpenAI API, LangChain, Python, MLOps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100
E050 | Abhishek Kulkarni | ml | Mid AI / ML Engineer | Mid | Pune | 6 | scikit-learn, OpenAI API, Python, LangChain | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E029 | Ritika Tiwari | mobile | Mid Mobile Developer | Mid | Pune | 4 | Kotlin, Offline sync, React Native, Google Maps SDK | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
E030 | Prachi Patidar | mobile | Mid Mobile Developer | Mid | Indore | 6 | Kotlin, Firebase, React Native, Offline sync | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E031 | Naveen Iyer | mobile | Mid Mobile Developer | Mid | Indore | 4 | Offline sync, Flutter, Firebase, React Native | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E032 | Ritika Rao | mobile | Junior Mobile Developer | Junior | Indore | 2 | Swift, Kotlin, Google Maps SDK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
E033 | Swati Sethi | mobile | Mid Mobile Developer | Mid | Indore | 4 | Offline sync, React Native, Firebase, Google Maps SDK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E034 | Vaishali Gupta | mobile | Junior Mobile Developer | Junior | Indore | 1 | React Native, Firebase, Kotlin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E001 | Saurabh Bhargava | pm | Senior Project Manager | Senior | Pune | 6 | HIPAA, Agile, Risk management, GDPR, Scrum | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E002 | Rajat Dubey | pm | Lead Project Manager | Lead | Indore | 12 | Risk management, Scrum, Jira, HIPAA, Client communication, Agile | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 100 | 100 | 100 | 100
E003 | Kriti Bhargava | pm | Senior Project Manager | Senior | Indore | 10 | HIPAA, Agile, Client communication, Jira, Risk management | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100
E004 | Rohan Raghuwanshi | pm | Senior Project Manager | Senior | Pune | 10 | Scrum, Jira, HIPAA, Agile, Risk management | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E035 | Bhavna Verma | qa | Mid QA Engineer | Mid | Indore | 4 | Security testing, API testing, Manual testing, Playwright | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 50 | 50 | 50 | 50 | 100
E036 | Priya Solanki | qa | Senior QA Engineer | Senior | Bhopal | 10 | JMeter, Security testing, Playwright, API testing, Selenium | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
E037 | Bhavna Goyal | qa | Mid QA Engineer | Mid | Indore | 4 | Selenium, Cypress, Appium, Playwright | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 100 | 100 | 100 | 100
E038 | Ritika Solanki | qa | Senior QA Engineer | Senior | Indore | 9 | Cypress, Security testing, Selenium, Manual testing, API testing | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
E039 | Gaurav Shinde | qa | Mid QA Engineer | Mid | Pune | 3 | API testing, Selenium, Security testing, Cypress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50
E040 | Tarun Khandelwal | qa | Senior QA Engineer | Senior | Pune | 11 | API testing, Playwright, Selenium, Appium, Cypress | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 100 | 100 | 100
E041 | Mohit Bhonsle | qa | Mid QA Engineer | Mid | Pune | 3 | Selenium, JMeter, API testing, Security testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E008 | Zoya Shukla | uiux | Senior UI/UX Designer | Senior | Pune | 8 | User research, Accessibility (WCAG), Design systems, Mobile UI, Prototyping | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100
E009 | Chirag Deshmukh | uiux | Junior UI/UX Designer | Junior | Bhopal | 3 | Accessibility (WCAG), User research, Figma | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
E010 | Pooja Patidar | uiux | Senior UI/UX Designer | Senior | Pune | 9 | Figma, Mobile UI, Accessibility (WCAG), Design systems, Prototyping | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Week columns start on the date shown (Monday). Values: % of the person's week not booked on projects or leave, from the demo assignments file.

## Module history
What past modules ACTUALLY took: median hours per role, normalised to medium complexity (demo)
Scale by complexity: low x0.6, medium x1.0, high x1.6. 'Overrun' = how far past estimates for this module were below actuals. Rows with 0 past projects show the catalog starting point instead.
Module key | Module | Past projects | Past overrun | Business Analyst | UI/UX Designer | Frontend Developer | Backend Developer | Mobile Developer | QA Engineer | DevOps / Cloud Engineer | Data / BI Engineer | AI / ML Engineer | Total (build)
admin_panel | Admin panel & back office | 8 | 17.5% | 19.6 | 29.9 | 99.1 | 88.5 |  | 48.4
auth | User accounts, login & roles | 17 | 17.3% | 9.2 | 14.4 | 48.3 | 65.8 |  | 29.1
booking | Booking & scheduling engine | 5 | 22.4% | 28.6 | 27.7 | 77.4 | 137.4 |  | 69.5
bpm | Workflow & approval engine (BPM) | 2 | 6.9% | 39.4 |  | 60.9 | 116.2 |  | 41
cloud_infra | Cloud infrastructure, CI/CD & environments | 7 | 20.3% |  |  |  | 19.8 |  |  | 100.7
cms | CMS & content management | 5 | 15.3% |  | 21.2 | 59.8 | 49.3 |  | 25.8
compliance | Audit logging & compliance controls | 9 | 20.2% | 19.1 |  |  | 76 |  | 29.9 | 30
crm | CRM workflows & customer records | 1 | 11.6% | 40.7 |  | 80 | 133.1 |  | 39.8
ecommerce | Product catalog, cart & checkout | 2 | 21.9% |  | 34.4 | 105.8 | 122.8 |  | 61.4
etl | Data pipeline / ETL | 7 | 14.2% |  |  |  | 28 |  | 26.8 | 17.5 | 133
geo | Maps, geolocation & route tracking | 3 | 23.6% |  |  | 52.3 | 69.7 | 49.2 | 30.7
integration | Third-party API integration | 10 | 23.8% | 14.4 |  |  | 89.5 |  | 29.4
iot | IoT device ingestion & telemetry | 3 | 18.8% |  |  |  | 120.5 |  | 41.5 | 55.2 | 50.1
llm_assistant | LLM assistant / RAG chatbot | 3 | 30.5% |  |  | 43.4 | 62.5 |  | 51.6 |  |  | 165.2
migration | Legacy data migration | 2 | 22.5% | 20 |  |  | 48.2 |  | 37.8 |  | 80.2
ml_model | Predictive ML model | 1 | 32% | [5 empty] | 38.8 |  | 83.5 | 236.6
mobile_app | Mobile app (iOS + Android, cross-platform) | 7 | 16.8% |  | 71.5 |  | 46.6 | 353.2 | 134.8
notifications | Notifications (email, SMS, push) | 6 | 19% |  |  |  | 45.5 | 18.4 | 18.6
patient_records | Patient records & care plans | 1 | 19.7% | 43.9 |  | 98.7 | 157.7 |  | 77.2
payments | Payments & billing integration | 7 | 21.2% | 17.1 |  | 37.2 | 111 |  | 55.3
realtime | Real-time sync & live updates | 4 | 9.9% |  |  | 44.3 | 89.4 |  | 33.8 | 18
reporting | Reporting & analytics dashboard | 11 | 14.1% |  | 19 | 60.7 | 45.1 |  | 27.9 |  | 46.6
search | Search, filters & listings | 6 | 18.8% |  |  | 47.2 | 59.9 |  | 21
tracking | Event tracking & pixel analytics | 2 | 10.9% |  |  |  | 82 |  | 24.3 | 34 | 80
web_portal | Customer-facing web portal (UI build) | 10 | 14.2% | 19.9 | 68.9 | 191.3 |  |  | 49.5

## Past projects
Past projects: estimated vs actual hours (demo)
ID | Project | Client | Country | Type | Stack | Contract | Cur. | Price | Est. hours | Actual hours | Overrun | Start | Actual end | Team | Modules | Notes
P101 | Patient portal v2 | CareBridge Health | US | web | .NET Core, React, SQL Server, Azure | fixed | USD | 64900 | 1972 | 2274 |  | 2023-02-06 | 2023-10-02 | 3 | auth, patient_records, booking, notifications, compliance, web_portal, cloud_infra | Delivered on time
P102 | Telehealth mobile app | CareBridge Health | US | mobile | React Native, Node.js, Twilio, AWS | tm | USD | 52100 | 1778 | 2092 |  | 2024-04-01 | 2024-11-04 | 3 | mobile_app, auth, booking, notifications, integration, compliance | App-store review added 2 weeks
P103 | Care-plan analytics dashboard | MediLink Partners | US | bi | Power BI, Azure SQL, Python | fixed | USD | 27500 | 773 | 819 |  | 2022-09-05 | 2022-12-26 | 3 | etl, reporting, auth, compliance | Delivered on time
P104 | Provider scheduling system | MediLink Partners | US | web | .NET Core, Angular, SQL Server | fixed | USD | 39800 | 1119 | 1312 |  | 2024-08-12 | 2025-01-27 | 3 | booking, auth, admin_panel, notifications, integration | UAT sign-off slow on client side
P105 | Wallets on the Fly | PayNest | UK | mobile | Flutter, Node.js, PostgreSQL, AWS | tm | GBP | 49300 | 2055 | 2475 |  | 2021-03-01 | 2022-01-10 | 3 | mobile_app, payments, auth, notifications, compliance, admin_panel | Device fragmentation drove extra QA
P106 | Merchant onboarding portal | PayNest | UK | web | React, .NET Core, Azure | fixed | GBP | 24400 | 950 | 1061 |  | 2023-10-02 | 2024-02-12 | 3 | web_portal, bpm, integration, auth | Scope creep in admin features
P107 | Machine monitoring dashboard | Kraftwerk Maschinenbau GmbH | DE | iot | Node.js, MQTT, InfluxDB, React, Azure | fixed | EUR | 33400 | 977 | 1101 |  | 2022-01-10 | 2022-07-11 | 3 | iot, reporting, realtime, auth, cloud_infra | Device firmware changes from client side
P108 | Spare-parts B2B ordering portal | Kraftwerk Maschinenbau GmbH | DE | ecommerce | .NET Core, Angular, SQL Server | fixed | EUR | 31000 | 1000 | 1181 |  | 2024-11-04 | 2025-04-07 | 3 | ecommerce, search, integration, auth, admin_panel | Catalog import edge cases
P109 | Coach booking platform | Coachline Travel | UK | web | PHP Laravel, Vue, MySQL, AWS | fixed | GBP | 39200 | 1508 | 1716 |  | 2019-06-03 | 2019-12-23 | 3 | booking, payments, search, web_portal, admin_panel, notifications | Delivered on time
P110 | Sightseeing tours mobile app | Coachline Travel | UK | mobile | React Native, Node.js, Stripe | fixed | GBP | 35700 | 1261 | 1525 |  | 2023-05-08 | 2023-10-09 | 3 | mobile_app, booking, payments, geo | Offline sync was underestimated
P111 | Adaptive learning platform (LMS) | BrightPath Learning | US | web | React, Python FastAPI, PostgreSQL, AWS | tm | USD | 39600 | 1290 | 1496 |  | 2022-07-11 | 2023-03-06 | 3 | web_portal, auth, cms, reporting, admin_panel | Scope creep in admin features
P112 | AI homework tutor (LLM) | BrightPath Learning | US | ai | Python, OpenAI API, RAG, React | tm | USD | 33200 | 968 | 1284 |  | 2025-01-13 | 2025-06-23 | 3 | llm_assistant, web_portal, auth, compliance | Hallucination guardrails added late
P113 | Live show story-sync app | StoryLive Media | US | mobile | React Native, Node.js, WebSockets, AWS | fixed | USD | 40200 | 1155 | 1397 |  | 2020-08-03 | 2020-12-07 | 3 | mobile_app, realtime, cms, cloud_infra | Offline sync was underestimated
P114 | Multi-time-zone live polling | StoryLive Media | US | web | React, Node.js, Redis, AWS Lambda | fixed | USD | 31700 | 886 | 1005 |  | 2023-01-09 | 2023-04-10 | 3 | realtime, web_portal, reporting, cloud_infra | UAT sign-off slow on client side
P115 | 50-state offender search | SafeWatch Registry | US | web | .NET Core, SQL Server, Elasticsearch, Azure | tm | USD | 37200 | 1226 | 1351 |  | 2019-02-04 | 2019-11-04 | 3 | search, etl, web_portal, compliance, geo | UAT sign-off slow on client side
P116 | Registry data-sync modernization | SafeWatch Registry | US | migration | .NET Core, Azure Functions, SQL Server | fixed | USD | 27900 | 730 | 930 |  | 2024-02-05 | 2024-07-29 | 3 | migration, etl, integration, cloud_infra | Cut-over weekend slipped once
P117 | Store performance BI | Vandenberg Retail NV | BE | bi | Power BI, Snowflake, Airflow | fixed | EUR | 22100 | 669 | 702 |  | 2022-03-07 | 2022-06-20 | 3 | etl, reporting, integration | Source data definitions unclear at start
P118 | Headless e-commerce storefront | Vandenberg Retail NV | BE | ecommerce | Next.js, Node.js, Stripe, AWS | fixed | EUR | 35300 | 1100 | 1303 |  | 2024-06-03 | 2024-12-09 | 3 | ecommerce, cms, payments, search, integration | Payment gateway certification delayed go-live
P119 | Fleet tracking app | Gulf Freight Lines | AE | mobile | Flutter, Node.js, Google Maps, AWS IoT | fixed | USD | 55300 | 1650 | 1933 |  | 2023-09-04 | 2024-03-18 | 3 | mobile_app, geo, iot, admin_panel, reporting | Offline sync was underestimated
P120 | Property listing portal | Outback Realty Group | AU | web | React, Node.js, PostgreSQL, AWS | fixed | AUD | 46000 | 928 | 1060 |  | 2022-10-03 | 2023-02-13 | 3 | search, web_portal, cms, auth, integration | Delivered on time
P121 | Claims processing portal | Kiwi Insure | NZ | web | .NET Core, Angular, SQL Server, Azure | fixed | NZD | 82000 | 1380 | 1560 |  | 2024-09-02 | 2025-03-31 | 3 | bpm, web_portal, migration, auth, compliance | Delivered on time
P122 | Marketplace MVP | CapeTech Ventures | ZA | web | React, Node.js, PostgreSQL, Stripe | fixed | USD | 25100 | 781 | 906 |  | 2025-02-03 | 2025-04-21 | 3 | web_portal, auth, payments, search, admin_panel | Scope creep in admin features
P123 | Fintech savings MVP | CapeTech Ventures | ZA | mobile | Flutter, Firebase, Stripe | fixed | USD | 24700 | 727 | 903 |  | 2025-06-02 | 2025-09-01 | 3 | mobile_app, auth, payments, notifications | App-store review added 2 weeks
P124 | Pixel tracking at scale | Pixelwise Analytics | US | bigdata | Node.js, Kafka, Spark, AWS | tm | USD | 37400 | 1037 | 1211 |  | 2017-04-03 | 2018-01-01 | 3 | tracking, etl, reporting, cloud_infra | Traffic spikes forced re-architecture of ingestion
P125 | 360 web monitoring dashboard | Pixelwise Analytics | US | bi | React, Python, ClickHouse, AWS | fixed | USD | 30400 | 878 | 899 |  | 2021-11-01 | 2022-03-07 | 3 | reporting, tracking, realtime, auth | Delivered on time
P126 | Smart-meter analytics | Nordlicht Energie AG | DE | iot | Python, Azure IoT Hub, Power BI | fixed | EUR | 39000 | 1150 | 1346 |  | 2024-10-07 | 2025-03-24 | 3 | iot, etl, reporting, compliance, cloud_infra | Field testing delayed by hardware shipping
P127 | Language-learning app | Sakura Learning KK | JP | mobile | React Native, Node.js, OpenAI API | tm | USD | 53400 | 1616 | 1946 |  | 2025-05-05 | 2025-12-08 | 3 | mobile_app, llm_assistant, auth, cms, payments | App-store review added 2 weeks
P128 | Sales CRM customization | MediLink Partners | US | crm | .NET Core, React, Salesforce API | fixed | USD | 29300 | 881 | 947 |  | 2025-03-03 | 2025-06-30 | 3 | crm, integration, reporting, auth | Salesforce API limits needed batching redesign
P129 | Demand forecasting model | Vandenberg Retail NV | BE | ai | Python, scikit-learn, Snowflake, AWS SageMaker | tm | EUR | 30400 | 828 | 1081 |  | 2025-07-07 | 2025-11-03 | 3 | ml_model, etl, reporting | Client changed the knowledge base mid-project
P130 | Customer support RAG assistant | PayNest | UK | ai | Python, OpenAI API, PostgreSQL pgvector, React | fixed | GBP | 26700 | 896 | 1162 |  | 2025-08-04 | 2025-12-01 | 3 | llm_assistant, integration, compliance, admin_panel | Client changed the knowledge base mid-project
All projects

## Past project modules
Project | Module | Complexity | Role | Est. hours | Actual hours
P101 | auth | high | ba | 13.7 | 15.2
P101 | auth | high | uiux | 20.5 | 22.8
P101 | auth | high | fe | 68.4 | 81.5
P101 | auth | high | be | 95.8 | 105.9
P101 | auth | high | qa | 41.1 | 44.4
P101 | patient_records | high | ba | 68.2 | 70.3
P101 | patient_records | high | fe | 136.4 | 157.9
P101 | patient_records | high | be | 204.6 | 252.3
P101 | patient_records | high | qa | 95.5 | 123.5
P101 | booking | medium | ba | 26.5 | 28.6
P101 | booking | medium | uiux | 26.5 | 27.8
P101 | booking | medium | fe | 70.5 | 83.5
P101 | booking | medium | be | 132.3 | 144.8
P101 | booking | medium | qa | 61.7 | 71.1
P101 | notifications | medium | be | 40.4 | 43.8
P101 | notifications | medium | mobile | 16.2 | 18.4
P101 | notifications | medium | qa | 16.2 | 19.6
P101 | compliance | high | ba | 27 | 29
P101 | compliance | high | be | 107.9 | 121.4
P101 | compliance | high | devops | 40.5 | 51.4
P101 | compliance | high | qa | 40.5 | 48.7
P101 | web_portal | medium | ba | 14.4 | 17.5
P101 | web_portal | medium | uiux | 54 | 63
P101 | web_portal | medium | fe | 144 | 166.7
P101 | web_portal | medium | qa | 36 | 46.1
P101 | cloud_infra | medium | be | 16.8 | 19.1
P101 | cloud_infra | medium | devops | 84 | 102.1
P101 | management | medium | pm | 170 | 191.2
P101 | management | medium | lead | 102 | 106.4
P102 | mobile_app | high | uiux | 89.3 | 101.1
P102 | mobile_app | high | mobile | 476.4 | 537
P102 | mobile_app | high | be | 59.5 | 63.5
P102 | mobile_app | high | qa | 178.6 | 215.6
P102 | auth | medium | ba | 8.1 | 10.3
P102 | auth | medium | uiux | 12.2 | 14.4
P102 | auth | medium | fe | 40.5 | 53.7
P102 | auth | medium | be | 56.7 | 65.6
P102 | auth | medium | qa | 24.3 | 31.7
P102 | booking | medium | ba | 23.2 | 25.2
P102 | booking | medium | uiux | 23.2 | 27.7
P102 | booking | medium | fe | 61.8 | 76.1
P102 | booking | medium | be | 115.8 | 137.4
P102 | booking | medium | qa | 54.1 | 70.8
P102 | notifications | medium | be | 43.7 | 52.1
P102 | notifications | medium | mobile | 17.5 | 22.2
P102 | notifications | medium | qa | 17.5 | 20.9
P102 | integration | medium | ba | 11.3 | 13.1
P102 | integration | medium | be | 67.6 | 88
P102 | integration | medium | qa | 22.5 | 26.9
P102 | compliance | medium | ba | 16.1 | 19.5
P102 | compliance | medium | be | 64.5 | 85.3
P102 | compliance | medium | devops | 24.2 | 32.1
P102 | compliance | medium | qa | 24.2 | 30.6
P102 | management | medium | pm | 153.3 | 174.9
P102 | management | medium | lead | 92 | 95.9
P103 | etl | medium | be | 25.9 | 28
P103 | etl | medium | data | 129.4 | 140.3
P103 | etl | medium | devops | 17.3 | 17.5
P103 | etl | medium | qa | 25.9 | 29.1
P103 | reporting | high | uiux | 22.5 | 22.6
P103 | reporting | high | fe | 78.8 | 82.5
P103 | reporting | high | be | 56.3 | 61.1
P103 | reporting | high | data | 56.3 | 59.1
P103 | reporting | high | qa | 33.8 | 35.2
P103 | auth | low | ba | 4.9 | 4.8
P103 | auth | low | uiux | 7.3 | 8.3
P103 | auth | low | fe | 24.4 | 26.7
P103 | auth | low | be | 34.1 | 36.1
P103 | auth | low | qa | 14.6 | 17.6
P103 | compliance | medium | ba | 16.9 | 14.9
P103 | compliance | medium | be | 67.6 | 60
P103 | compliance | medium | devops | 25.3 | 25.6
P103 | compliance | medium | qa | 25.3 | 28.2
P103 | management | medium | pm | 66.7 | 74.3
P103 | management | medium | lead | 40 | 47.1
P104 | booking | high | ba | 35.7 | 45.9
P104 | booking | high | uiux | 35.7 | 42.5
P104 | booking | high | fe | 95.1 | 106.7
P104 | booking | high | be | 178.3 | 198.4
P104 | booking | high | qa | 83.2 | 91.1
P104 | auth | medium | ba | 8.4 | 9.3
P104 | auth | medium | uiux | 12.5 | 14.6
P104 | auth | medium | fe | 41.8 | 47.5
P104 | auth | medium | be | 58.5 | 68.3
P104 | auth | medium | qa | 25.1 | 30.2
P104 | admin_panel | medium | ba | 17.1 | 19.1
P104 | admin_panel | medium | uiux | 25.7 | 31.9
P104 | admin_panel | medium | fe | 85.7 | 111.5
P104 | admin_panel | medium | be | 77.1 | 99.9
P104 | admin_panel | medium | qa | 42.8 | 49.2
P104 | notifications | low | be | 22.1 | 22.7
P104 | notifications | low | mobile | 8.8 | 10.8
P104 | notifications | low | qa | 8.8 | 11.5
P104 | integration | medium | ba | 11.4 | 15.9
P104 | integration | medium | be | 68.4 | 83
P104 | integration | medium | qa | 22.8 | 28.7
P104 | management | medium | pm | 96.5 | 112.6
P104 | management | medium | lead | 57.9 | 60.5
P105 | mobile_app | high | uiux | 82.2 | 108.5
P105 | mobile_app | high | mobile | 438.4 | 562.8
P105 | mobile_app | high | be | 54.8 | 72.7
P105 | mobile_app | high | qa | 164.4 | 183.7
P105 | payments | high | ba | 23.1 | 27.4
P105 | payments | high | fe | 46.2 | 53.8
P105 | payments | high | be | 138.5 | 149.1
P105 | payments | high | qa | 69.3 | 88.3
P105 | auth | high | ba | 14.2 | 16.3
P105 | auth | high | uiux | 21.2 | 25.4
P105 | auth | high | fe | 70.8 | 86.8
P105 | auth | high | be | 99.1 | 122.7
P105 | auth | high | qa | 42.5 | 54.7
P105 | notifications | medium | be | 38.6 | 47.1
P105 | notifications | medium | mobile | 15.4 | 18.5
P105 | notifications | medium | qa | 15.4 | 17
P105 | compliance | high | ba | 25.2 | 30.5
P105 | compliance | high | be | 100.8 | 121.6
P105 | compliance | high | devops | 37.8 | 46
P105 | compliance | high | qa | 37.8 | 47.2
P105 | admin_panel | medium | ba | 16.2 | 22.2
P105 | admin_panel | medium | uiux | 24.4 | 29.9
P105 | admin_panel | medium | fe | 81.2 | 98.8
P105 | admin_panel | medium | be | 73.1 | 84.7
P105 | admin_panel | medium | qa | 40.6 | 49.4
P105 | management | medium | pm | 177.1 | 195.6
P105 | management | medium | lead | 106.3 | 114.6
P106 | web_portal | medium | ba | 15.7 | 19.1
P106 | web_portal | medium | uiux | 58.9 | 62.1
P106 | web_portal | medium | fe | 157 | 185.3
P106 | web_portal | medium | qa | 39.3 | 38.2
P106 | bpm | medium | ba | 31.4 | 36.3
P106 | bpm | medium | fe | 55 | 57.7
P106 | bpm | medium | be | 102.1 | 97.2
P106 | bpm | medium | qa | 39.3 | 41.3
P106 | integration | high | ba | 18.9 | 23.5
P106 | integration | high | be | 113.3 | 135.6
P106 | integration | high | qa | 37.8 | 48.3
P106 | auth | medium | ba | 8.6 | 9.4
P106 | auth | medium | uiux | 12.9 | 14.4
P106 | auth | medium | fe | 43 | 54
P106 | auth | medium | be | 60.2 | 65.6
P106 | auth | medium | qa | 25.8 | 30.9
P106 | management | medium | pm | 81.9 | 91.4
P106 | management | medium | lead | 49.2 | 50.4
P107 | iot | high | be | 137.3 | 170.2
P107 | iot | high | data | 57.2 | 61.6
P107 | iot | high | devops | 57.2 | 61.7
P107 | iot | high | qa | 45.8 | 50.5
P107 | reporting | medium | uiux | 17.1 | 21.5
P107 | reporting | medium | fe | 60 | 63.1
P107 | reporting | medium | be | 42.8 | 49.5
P107 | reporting | medium | data | 42.8 | 50.1
P107 | reporting | medium | qa | 25.7 | 31.5
P107 | realtime | medium | fe | 39.3 | 44.2
P107 | realtime | medium | be | 78.6 | 84
P107 | realtime | medium | devops | 15.7 | 18.4
P107 | realtime | medium | qa | 31.4 | 35.8
P107 | auth | low | ba | 5.2 | 5.5
P107 | auth | low | uiux | 7.8 | 9.3
P107 | auth | low | fe | 25.9 | 29.9
P107 | auth | low | be | 36.3 | 36.5
P107 | auth | low | qa | 15.5 | 16.3
P107 | cloud_infra | medium | be | 16.7 | 19.5
P107 | cloud_infra | medium | devops | 83.5 | 100.7
P107 | management | medium | pm | 84.2 | 86.6
P107 | management | medium | lead | 50.5 | 54.7
P108 | ecommerce | medium | uiux | 31.2 | 38.7
P108 | ecommerce | medium | fe | 93.6 | 119.6
P108 | ecommerce | medium | be | 101.4 | 127.3
P108 | ecommerce | medium | qa | 54.6 | 63.8
P108 | search | medium | fe | 37.8 | 50.9
P108 | search | medium | be | 52.9 | 60.7
P108 | search | medium | qa | 18.9 | 22.3
P108 | integration | high | ba | 20 | 22.7
P108 | integration | high | be | 120.3 | 138
P108 | integration | high | qa | 40.1 | 44.3
P108 | auth | medium | ba | 8.1 | 8.5
P108 | auth | medium | uiux | 12.1 | 14.1
P108 | auth | medium | fe | 40.3 | 50.9
P108 | auth | medium | be | 56.4 | 65.1
P108 | auth | medium | qa | 24.2 | 27.9
P108 | admin_panel | low | ba | 10.3 | 11.4
P108 | admin_panel | low | uiux | 15.5 | 17.9
P108 | admin_panel | low | fe | 51.7 | 51.2
P108 | admin_panel | low | be | 46.6 | 57
P108 | admin_panel | low | qa | 25.9 | 28.5
P108 | management | medium | pm | 86.2 | 102.2
P108 | management | medium | lead | 51.7 | 58.3
P109 | booking | high | ba | 37.1 | 43.9
P109 | booking | high | uiux | 37.1 | 45.5
P109 | booking | high | fe | 98.9 | 123.8
P109 | booking | high | be | 185.5 | 212.5
P109 | booking | high | qa | 86.5 | 96.6
P109 | payments | medium | ba | 17.9 | 20.8
P109 | payments | medium | fe | 35.7 | 37.5
P109 | payments | medium | be | 107.1 | 127.1
P109 | payments | medium | qa | 53.6 | 64.3
P109 | search | medium | fe | 34 | 36
P109 | search | medium | be | 47.6 | 54
P109 | search | medium | qa | 17 | 18
P109 | web_portal | medium | ba | 14.2 | 16.9
P109 | web_portal | medium | uiux | 53.3 | 60.7
P109 | web_portal | medium | fe | 142.1 | 148.4
P109 | web_portal | medium | qa | 35.5 | 40.4
P109 | admin_panel | medium | ba | 17.9 | 20
P109 | admin_panel | medium | uiux | 26.9 | 30.1
P109 | admin_panel | medium | fe | 89.6 | 111.2
P109 | admin_panel | medium | be | 80.6 | 86.9
P109 | admin_panel | medium | qa | 44.8 | 40.6
P109 | notifications | low | be | 20.4 | 26.1
P109 | notifications | low | mobile | 8.2 | 9.1
P109 | notifications | low | qa | 8.2 | 10.2
P109 | management | medium | pm | 130 | 144.9
P109 | management | medium | lead | 78 | 90
P110 | mobile_app | medium | uiux | 52.1 | 58.5
P110 | mobile_app | medium | mobile | 277.8 | 326.5
P110 | mobile_app | medium | be | 34.7 | 43.9
P110 | mobile_app | medium | qa | 104.2 | 119.6
P110 | booking | medium | ba | 24.1 | 33.4
P110 | booking | medium | uiux | 24.1 | 27.5
P110 | booking | medium | fe | 64.2 | 93
P110 | booking | medium | be | 120.3 | 153
P110 | booking | medium | qa | 56.1 | 69.5
P110 | payments | medium | ba | 13.6 | 15.5
P110 | payments | medium | fe | 27.2 | 31.4
P110 | payments | medium | be | 81.6 | 96.9
P110 | payments | medium | qa | 40.8 | 51.8
P110 | geo | medium | fe | 41.6 | 54
P110 | geo | medium | be | 58.3 | 71.4
P110 | geo | medium | mobile | 41.6 | 56.7
P110 | geo | medium | qa | 25 | 32.4
P110 | management | medium | pm | 108.7 | 116.6
P110 | management | medium | lead | 65.2 | 73.4
P111 | web_portal | high | ba | 26.3 | 28.1
P111 | web_portal | high | uiux | 98.8 | 126.1
P111 | web_portal | high | fe | 263.5 | 331.3
P111 | web_portal | high | qa | 65.9 | 88.5
P111 | auth | medium | ba | 8.6 | 9.2
P111 | auth | medium | uiux | 13 | 15
P111 | auth | medium | fe | 43.2 | 44.5
P111 | auth | medium | be | 60.5 | 70.9
P111 | auth | medium | qa | 25.9 | 29.1
P111 | cms | medium | uiux | 15 | 15.2
P111 | cms | medium | fe | 45 | 49
P111 | cms | medium | be | 37.5 | 49.3
P111 | cms | medium | qa | 18.7 | 21
P111 | reporting | medium | uiux | 15.9 | 18.4
P111 | reporting | medium | fe | 55.5 | 60.7
P111 | reporting | medium | be | 39.7 | 45.1
P111 | reporting | medium | data | 39.7 | 41
P111 | reporting | medium | qa | 23.8 | 26.2
P111 | admin_panel | medium | ba | 14.8 | 16.7
P111 | admin_panel | medium | uiux | 22.3 | 27.3
P111 | admin_panel | medium | fe | 74.2 | 74.2
P111 | admin_panel | medium | be | 66.8 | 68
P111 | admin_panel | medium | qa | 37.1 | 40.1
P111 | management | medium | pm | 111.2 | 126.5
P111 | management | medium | lead | 66.7 | 74.5
P112 | llm_assistant | high | fe | 53.2 | 77
P112 | llm_assistant | high | be | 79.8 | 118
P112 | llm_assistant | high | ml | 232.9 | 318.9
P112 | llm_assistant | high | qa | 66.5 | 94.6
P112 | web_portal | low | ba | 10.2 | 13.3
P112 | web_portal | low | uiux | 38.3 | 50.7
P112 | web_portal | low | fe | 102.1 | 131.4
P112 | web_portal | low | qa | 25.5 | 36.9
P112 | auth | low | ba | 4.5 | 6.4
P112 | auth | low | uiux | 6.8 | 9.5
P112 | auth | low | fe | 22.6 | 29
P112 | auth | low | be | 31.7 | 39.5
P112 | auth | low | qa | 13.6 | 20.3
P112 | compliance | medium | ba | 18.4 | 24.1
P112 | compliance | medium | be | 73.5 | 97.7
P112 | compliance | medium | devops | 27.6 | 32.6
P112 | compliance | medium | qa | 27.6 | 29.9
P112 | management | medium | pm | 83.5 | 94.9
P112 | management | medium | lead | 50.1 | 58.9
P113 | mobile_app | medium | uiux | 58.7 | 73.5
P113 | mobile_app | medium | mobile | 313.2 | 388.7
P113 | mobile_app | medium | be | 39.2 | 46.6
P113 | mobile_app | medium | qa | 117.5 | 139.1
P113 | realtime | high | fe | 55.3 | 71.1
P113 | realtime | high | be | 110.5 | 148.8
P113 | realtime | high | devops | 22.1 | 28.3
P113 | realtime | high | qa | 44.2 | 47.5
P113 | cms | medium | uiux | 18.1 | 22.9
P113 | cms | medium | fe | 54.2 | 65.5
P113 | cms | medium | be | 45.1 | 63.4
P113 | cms | medium | qa | 22.6 | 25.8
P113 | cloud_infra | medium | be | 15.8 | 19.8
P113 | cloud_infra | medium | devops | 79.1 | 85.4
P113 | management | medium | pm | 99.6 | 100.4
P113 | management | medium | lead | 59.7 | 69.8
P114 | realtime | high | fe | 68.2 | 79.1
P114 | realtime | high | be | 136.4 | 156.2
P114 | realtime | high | devops | 27.3 | 36.9
P114 | realtime | high | qa | 54.5 | 50.8
P114 | web_portal | low | ba | 10.9 | 12.6
P114 | web_portal | low | uiux | 41 | 48.8
P114 | web_portal | low | fe | 109.3 | 119.5
P114 | web_portal | low | qa | 27.3 | 31.4
P114 | reporting | low | uiux | 10.5 | 12.9
P114 | reporting | low | fe | 36.8 | 41.2
P114 | reporting | low | be | 26.3 | 32.2
P114 | reporting | low | data | 26.3 | 32.2
P114 | reporting | low | qa | 15.8 | 19.9
P114 | cloud_infra | high | be | 28.9 | 38.2
P114 | cloud_infra | high | devops | 144.5 | 163
P114 | management | medium | pm | 76.4 | 84
P114 | management | medium | lead | 45.8 | 46.4
P115 | search | high | fe | 64.6 | 78.7
P115 | search | high | be | 90.4 | 101.3
P115 | search | high | qa | 32.3 | 33.8
P115 | etl | high | be | 37.5 | 44.8
P115 | etl | high | data | 187.7 | 192.8
P115 | etl | high | devops | 25 | 25.3
P115 | etl | high | qa | 37.5 | 42.8
P115 | web_portal | medium | ba | 15.3 | 16.7
P115 | web_portal | medium | uiux | 57.3 | 63
P115 | web_portal | medium | fe | 152.7 | 156.8
P115 | web_portal | medium | qa | 38.2 | 45.6
P115 | compliance | high | ba | 22.6 | 26.6
P115 | compliance | high | be | 90.5 | 100.8
P115 | compliance | high | devops | 33.9 | 37.8
P115 | compliance | high | qa | 33.9 | 40.1
P115 | geo | medium | fe | 34.3 | 38.1
P115 | geo | medium | be | 48 | 59.3
P115 | geo | medium | mobile | 34.3 | 38.9
P115 | geo | medium | qa | 20.6 | 25
P115 | management | medium | pm | 105.7 | 113.1
P115 | management | medium | lead | 63.4 | 69.4
P116 | migration | high | ba | 27 | 37.9
P116 | migration | high | be | 67.4 | 87.2
P116 | migration | high | data | 107.8 | 140
P116 | migration | high | qa | 53.9 | 67.3
P116 | etl | medium | be | 20.9 | 28.5
P116 | etl | medium | data | 104.7 | 133
P116 | etl | medium | devops | 14 | 20.2
P116 | etl | medium | qa | 20.9 | 26.8
P116 | integration | medium | ba | 12.1 | 16
P116 | integration | medium | be | 72.7 | 100.2
P116 | integration | medium | qa | 24.2 | 30.1
P116 | cloud_infra | medium | be | 17.3 | 22
P116 | cloud_infra | medium | devops | 86.3 | 105.7
P116 | management | medium | pm | 62.9 | 74.8
P116 | management | medium | lead | 37.8 | 40
P117 | etl | high | be | 33.7 | 35.7
P117 | etl | high | data | 168.3 | 174.2
P117 | etl | high | devops | 22.4 | 22.8
P117 | etl | high | qa | 33.7 | 37.6
P117 | reporting | high | uiux | 22.4 | 22.9
P117 | reporting | high | fe | 78.4 | 83.7
P117 | reporting | high | be | 56 | 57.2
P117 | reporting | high | data | 56 | 47.6
P117 | reporting | high | qa | 33.6 | 40.4
P117 | integration | low | ba | 8.1 | 8.2
P117 | integration | low | be | 48.4 | 54.6
P117 | integration | low | qa | 16.1 | 15.8
P117 | management | medium | pm | 57.7 | 59.8
P117 | management | medium | lead | 34.6 | 41.3
P118 | ecommerce | high | uiux | 44.7 | 48.2
P118 | ecommerce | high | fe | 134 | 147.2
P118 | ecommerce | high | be | 145.2 | 189.3
P118 | ecommerce | high | qa | 78.2 | 94.5
P118 | cms | medium | uiux | 17.5 | 21.2
P118 | cms | medium | fe | 52.4 | 65.3
P118 | cms | medium | be | 43.7 | 45.5
P118 | cms | medium | qa | 21.8 | 26.1
P118 | payments | medium | ba | 13.9 | 15.5
P118 | payments | medium | fe | 27.7 | 34.5
P118 | payments | medium | be | 83.2 | 92.8
P118 | payments | medium | qa | 41.6 | 52.3
P118 | search | medium | fe | 41.3 | 49.4
P118 | search | medium | be | 57.8 | 76.4
P118 | search | medium | qa | 20.6 | 25
P118 | integration | medium | ba | 13.8 | 15.9
P118 | integration | medium | be | 82.8 | 108.2
P118 | integration | medium | qa | 27.6 | 32.3
P118 | management | medium | pm | 94.8 | 100.4
P118 | management | medium | lead | 56.9 | 63.5
P119 | mobile_app | medium | uiux | 64.2 | 79.6
P119 | mobile_app | medium | mobile | 342.2 | 368.1
P119 | mobile_app | medium | be | 42.8 | 56.3
P119 | mobile_app | medium | qa | 128.3 | 152.7
P119 | geo | high | fe | 65.3 | 83.7
P119 | geo | high | be | 91.5 | 111.5
P119 | geo | high | mobile | 65.3 | 78.7
P119 | geo | high | qa | 39.2 | 49.1
P119 | iot | medium | be | 103.8 | 136.3
P119 | iot | medium | data | 43.3 | 50.1
P119 | iot | medium | devops | 43.3 | 57.5
P119 | iot | medium | qa | 34.6 | 41.5
P119 | admin_panel | medium | ba | 16.4 | 20
P119 | admin_panel | medium | uiux | 24.6 | 29.8
P119 | admin_panel | medium | fe | 82 | 99.4
P119 | admin_panel | medium | be | 73.8 | 90.1
P119 | admin_panel | medium | qa | 41 | 51.5
P119 | reporting | low | uiux | 11 | 12.8
P119 | reporting | low | fe | 38.5 | 42.9
P119 | reporting | low | be | 27.5 | 32.9
P119 | reporting | low | data | 27.5 | 33.8
P119 | reporting | low | qa | 16.5 | 20.8
P119 | management | medium | pm | 142.3 | 147.5
P119 | management | medium | lead | 85.4 | 86
P120 | search | high | fe | 56.1 | 72.5
P120 | search | high | be | 78.6 | 88.1
P120 | search | high | qa | 28.1 | 29.3
P120 | web_portal | medium | ba | 17.7 | 20.6
P120 | web_portal | medium | uiux | 66.4 | 73.9
P120 | web_portal | medium | fe | 177 | 197.3
P120 | web_portal | medium | qa | 44.2 | 48.8
P120 | cms | medium | uiux | 18.2 | 21.7
P120 | cms | medium | fe | 54.6 | 59.8
P120 | cms | medium | be | 45.5 | 57.3
P120 | cms | medium | qa | 22.8 | 27.8
P120 | auth | medium | ba | 6.9 | 7.7
P120 | auth | medium | uiux | 10.3 | 12.4
P120 | auth | medium | fe | 34.5 | 36.4
P120 | auth | medium | be | 48.2 | 52.3
P120 | auth | medium | qa | 20.7 | 27.6
P120 | integration | low | ba | 7.8 | 8.5
P120 | integration | low | be | 46.9 | 59.7
P120 | integration | low | qa | 15.6 | 19.6
P120 | management | medium | pm | 80 | 82.1
P120 | management | medium | lead | 48 | 56.7
P121 | bpm | high | ba | 56 | 68
P121 | bpm | high | fe | 98 | 102.7
P121 | bpm | high | be | 182.1 | 216.3
P121 | bpm | high | qa | 70 | 65
P121 | web_portal | medium | ba | 17.1 | 21
P121 | web_portal | medium | uiux | 64.2 | 72.7
P121 | web_portal | medium | fe | 171.2 | 181.2
P121 | web_portal | medium | qa | 42.8 | 50.1
P121 | migration | high | ba | 24.2 | 26
P121 | migration | high | be | 60.5 | 67
P121 | migration | high | data | 96.9 | 116.7
P121 | migration | high | qa | 48.4 | 53.5
P121 | auth | medium | ba | 7.9 | 8.3
P121 | auth | medium | uiux | 11.8 | 12.9
P121 | auth | medium | fe | 39.4 | 45.6
P121 | auth | medium | be | 55.1 | 65.9
P121 | auth | medium | qa | 23.6 | 26.4
P121 | compliance | medium | ba | 15 | 17.7
P121 | compliance | medium | be | 60.1 | 72.3
P121 | compliance | medium | devops | 22.5 | 24.5
P121 | compliance | medium | qa | 22.5 | 27.9
P121 | management | medium | pm | 118.9 | 134.5
P121 | management | medium | lead | 71.4 | 83.5
P122 | web_portal | low | ba | 10.9 | 13.8
P122 | web_portal | low | uiux | 41 | 39.1
P122 | web_portal | low | fe | 109.4 | 132.1
P122 | web_portal | low | qa | 27.4 | 30.5
P122 | auth | low | ba | 5.5 | 6.1
P122 | auth | low | uiux | 8.3 | 9.5
P122 | auth | low | fe | 27.6 | 28.2
P122 | auth | low | be | 38.6 | 39.6
P122 | auth | low | qa | 16.5 | 19.4
P122 | payments | medium | ba | 17 | 21
P122 | payments | medium | fe | 34 | 37.5
P122 | payments | medium | be | 101.9 | 130.2
P122 | payments | medium | qa | 51 | 65
P122 | search | low | fe | 22 | 25.5
P122 | search | low | be | 30.7 | 35.4
P122 | search | low | qa | 11 | 12.5
P122 | admin_panel | low | ba | 8.3 | 10.1
P122 | admin_panel | low | uiux | 12.5 | 14.7
P122 | admin_panel | low | fe | 41.5 | 46.1
P122 | admin_panel | low | be | 37.4 | 41.7
P122 | admin_panel | low | qa | 20.8 | 23.7
P122 | management | medium | pm | 67.3 | 76.5
P122 | management | medium | lead | 40.4 | 47.6
P123 | mobile_app | low | uiux | 34.6 | 42.9
P123 | mobile_app | low | mobile | 184.5 | 235.9
P123 | mobile_app | low | be | 23.1 | 29.3
P123 | mobile_app | low | qa | 69.2 | 74.5
P123 | auth | low | ba | 4.8 | 5.5
P123 | auth | low | uiux | 7.2 | 9.4
P123 | auth | low | fe | 24 | 31.4
P123 | auth | low | be | 33.6 | 42.4
P123 | auth | low | qa | 14.4 | 15.1
P123 | payments | medium | ba | 15.8 | 16.8
P123 | payments | medium | fe | 31.7 | 41.9
P123 | payments | medium | be | 95 | 129.9
P123 | payments | medium | qa | 47.5 | 68.7
P123 | notifications | low | be | 23 | 28.5
P123 | notifications | low | mobile | 9.2 | 11.5
P123 | notifications | low | qa | 9.2 | 10.8
P123 | management | medium | pm | 62.7 | 68.4
P123 | management | medium | lead | 37.6 | 39.7
P124 | tracking | high | be | 112.5 | 140
P124 | tracking | high | data | 112.5 | 136.6
P124 | tracking | high | devops | 45 | 58.5
P124 | tracking | high | qa | 33.7 | 39
P124 | etl | high | be | 36.4 | 42.1
P124 | etl | high | data | 181.9 | 196.7
P124 | etl | high | devops | 24.3 | 25.7
P124 | etl | high | qa | 36.4 | 44.8
P124 | reporting | medium | uiux | 14.1 | 17.6
P124 | reporting | medium | fe | 49.3 | 57.3
P124 | reporting | medium | be | 35.2 | 41.7
P124 | reporting | medium | data | 35.2 | 42.3
P124 | reporting | medium | qa | 21.1 | 27.7
P124 | cloud_infra | high | be | 26.1 | 31.8
P124 | cloud_infra | high | devops | 130.6 | 159.6
P124 | management | medium | pm | 89.4 | 89.7
P124 | management | medium | lead | 53.7 | 59.6
P125 | reporting | high | uiux | 27.6 | 30.4
P125 | reporting | high | fe | 96.7 | 93.4
P125 | reporting | high | be | 69.1 | 65.4
P125 | reporting | high | data | 69.1 | 74.5
P125 | reporting | high | qa | 41.4 | 44.6
P125 | tracking | medium | be | 76.9 | 76.4
P125 | tracking | medium | data | 76.9 | 74.6
P125 | tracking | medium | devops | 30.7 | 31.4
P125 | tracking | medium | qa | 23.1 | 24.3
P125 | realtime | medium | fe | 41.1 | 43.2
P125 | realtime | medium | be | 82.3 | 85.8
P125 | realtime | medium | devops | 16.5 | 15.5
P125 | realtime | medium | qa | 32.9 | 36.7
P125 | auth | low | ba | 4.2 | 4.7
P125 | auth | low | uiux | 6.2 | 6.5
P125 | auth | low | fe | 20.8 | 19.5
P125 | auth | low | be | 29.1 | 29.2
P125 | auth | low | qa | 12.5 | 14.3
P125 | management | medium | pm | 75.7 | 82.9
P125 | management | medium | lead | 45.4 | 45.4
P126 | iot | high | be | 172.3 | 192.8
P126 | iot | high | data | 71.8 | 81.1
P126 | iot | high | devops | 71.8 | 88.3
P126 | iot | high | qa | 57.4 | 71.5
P126 | etl | medium | be | 24 | 29.3
P126 | etl | medium | data | 119.8 | 155.9
P126 | etl | medium | devops | 16 | 19.1
P126 | etl | medium | qa | 24 | 26.7
P126 | reporting | medium | uiux | 17.7 | 21.5
P126 | reporting | medium | fe | 62 | 82
P126 | reporting | medium | be | 44.3 | 47.7
P126 | reporting | medium | data | 44.3 | 54.1
P126 | reporting | medium | qa | 26.6 | 33.1
P126 | compliance | medium | ba | 18.2 | 20.1
P126 | compliance | medium | be | 72.9 | 80.4
P126 | compliance | medium | devops | 27.4 | 30.6
P126 | compliance | medium | qa | 27.4 | 33.4
P126 | cloud_infra | medium | be | 15.5 | 18.5
P126 | cloud_infra | medium | devops | 77.5 | 88.2
P126 | management | medium | pm | 99.1 | 109.7
P126 | management | medium | lead | 59.5 | 61.9
P127 | mobile_app | high | uiux | 93.9 | 115.2
P127 | mobile_app | high | mobile | 501 | 565.2
P127 | mobile_app | high | be | 62.6 | 87.5
P127 | mobile_app | high | qa | 187.9 | 244.2
P127 | llm_assistant | medium | fe | 28.3 | 38.3
P127 | llm_assistant | medium | be | 42.5 | 53.1
P127 | llm_assistant | medium | ml | 123.9 | 164
P127 | llm_assistant | medium | qa | 35.4 | 41.3
P127 | auth | low | ba | 5.3 | 5.8
P127 | auth | low | uiux | 8 | 10.2
P127 | auth | low | fe | 26.5 | 33.4
P127 | auth | low | be | 37.1 | 42.7
P127 | auth | low | qa | 15.9 | 19.6
P127 | cms | medium | uiux | 14.9 | 18.7
P127 | cms | medium | fe | 44.6 | 58
P127 | cms | medium | be | 37.2 | 43.5
P127 | cms | medium | qa | 18.6 | 22.3
P127 | payments | low | ba | 9.1 | 11.4
P127 | payments | low | fe | 18.2 | 22.3
P127 | payments | low | be | 54.6 | 66.6
P127 | payments | low | qa | 27.3 | 33.2
P127 | management | medium | pm | 139.3 | 165.6
P127 | management | medium | lead | 83.6 | 84.1
P128 | crm | high | ba | 58.1 | 65.1
P128 | crm | high | fe | 116.2 | 128
P128 | crm | high | be | 174.3 | 213
P128 | crm | high | qa | 72.6 | 63.6
P128 | integration | high | ba | 18.9 | 21.8
P128 | integration | high | be | 113.5 | 100.4
P128 | integration | high | qa | 37.8 | 41.9
P128 | reporting | low | uiux | 8.7 | 9
P128 | reporting | low | fe | 30.4 | 28.8
P128 | reporting | low | be | 21.7 | 21.3
P128 | reporting | low | data | 21.7 | 25.3
P128 | reporting | low | qa | 13 | 16.1
P128 | auth | low | ba | 4.1 | 5.1
P128 | auth | low | uiux | 6.2 | 7.2
P128 | auth | low | fe | 20.6 | 22.6
P128 | auth | low | be | 28.9 | 27.7
P128 | auth | low | qa | 12.4 | 13.6
P128 | management | medium | pm | 75.9 | 82.4
P128 | management | medium | lead | 45.5 | 53.8
P129 | ml_model | high | data | 107 | 133.6
P129 | ml_model | high | ml | 285.2 | 378.5
P129 | ml_model | high | qa | 42.8 | 62
P129 | etl | medium | be | 24 | 29.6
P129 | etl | medium | data | 119.8 | 176.2
P129 | etl | medium | devops | 16 | 18.8
P129 | etl | medium | qa | 24 | 31
P129 | reporting | low | uiux | 8.7 | 11.8
P129 | reporting | low | fe | 30.3 | 36.6
P129 | reporting | low | be | 21.6 | 28.3
P129 | reporting | low | data | 21.6 | 29.5
P129 | reporting | low | qa | 13 | 17
P129 | management | medium | pm | 71.4 | 81.4
P129 | management | medium | lead | 42.8 | 47
P130 | llm_assistant | high | fe | 48.7 | 69.5
P130 | llm_assistant | high | be | 73 | 100
P130 | llm_assistant | high | ml | 213 | 264.3
P130 | llm_assistant | high | qa | 60.9 | 82.5
P130 | integration | medium | ba | 11.1 | 15
P130 | integration | medium | be | 66.8 | 100.1
P130 | integration | medium | qa | 22.3 | 30.9
P130 | compliance | medium | ba | 15.3 | 20.4
P130 | compliance | medium | be | 61.2 | 82.6
P130 | compliance | medium | devops | 22.9 | 30
P130 | compliance | medium | qa | 22.9 | 32.1
P130 | admin_panel | low | ba | 10.6 | 14.7
P130 | admin_panel | low | uiux | 16 | 24.4
P130 | admin_panel | low | fe | 53.2 | 69.9
P130 | admin_panel | low | be | 47.9 | 67.9
P130 | admin_panel | low | qa | 26.6 | 32.5
P130 | management | medium | pm | 77.2 | 77.5
P130 | management | medium | lead | 46.3 | 47.9